## GENERAL
NO. | JOB/ RELATING PARTIES | PIC | DEADLINE (TENTATIVE) | UPDATE/ NOTE (IF ANY)
1 | PO 106: Must be available in AUG (or client will choose Other contractors) | Mr. Nguyen/ Mr. Thang | 1st week of AUG | Reparing session is completed now, waiting for APAS => INV issuance
2 | SPR of Spare parts for HOANG LONG CLINIC | Ms. Hoa/ Mr. Duc Tran | Within today | Preparing SC session is completed already, Mr. Duc Tran and Mr. Don will come to visit client and finalize today
3 | Pending more than 200 Scopes: Plan to repair | Mr. Nguyen/ Mr. Thang | Within this month (AUG) | 17 scopes of Bach Mai Hospital: send quot within today
4 | HMU: Main PCB is usually out of order => Discuss about the root of the problem with HMU and solution to prevent/ reduce | Mr. Thang/ Mr. Hoang | Within this month (AUG) | - Hire 3rd party to survey? Mr. Kodama will get a tool to test the high currrent from Japan in next week? - Ngan will raise APAS to buy isolation transformer, power socked, electric wire and box to contain: within today
5 | Discuss about Adding Dealer information into EXFM system to extract into Master List file | Mr. Nguyen/ Mr. Thang | Within next week (from 07-11/AUG) | Need to discuss about RULE of INPUT INFORMATION: Remind FSE to input Dealer name as Contact Name
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Part Processing Update
WTY
NO. | JOB/ RELATING PARTIES | Equipment | PIC | DEADLINE (TENTATIVE) | UPDATE/ NOTE (IF ANY)
1 | Thai Binh Hospital (03 Scopes) | EC-530WL3,KC643K248 EG-530WR,LG361K352 EG-530WR,LG361K357 | Mr. Thang | Within next week (from 31/7 to 04/8)
4
5
6
7
8
PO
NO. | JOB/ RELATING PARTIES | Equipment | PIC | DEADLINE (TENTATIVE) | UPDATE/ NOTE (IF ANY)
109 | 07 fixed assets Stock-up | FFVN (EC-760ZP-V/M, 2C730K027) FTYO (EC-760ZP-V/M, 2C730K032) FFVN (EG-530WR, 2G361K546) FFVN (EC-530WI, 1C603K041) FTYO (EN-580T, 1C675K021) FFVN (EG-760Z, 8G403K090) FFVN (EC-760ZP V/M, 2C730K019) | Mr. Nguyen, Mr. Thang | Within next week (from 07-11/AUG) | Part is available now
110 | Preparation |  | Mr. Nguyen, Mr. Thang, Ngan | Within next week (from 07-11/AUG) | Mr. Nguyen prepared a list for South Side already, Mr. Thang will update accordingly after getting approval of Ms. Hoa/ Kodama san to repair FFVN's FA

## IN & OUT CONTROL
NO. | JOB/ RELATING PARTIES | PIC | DEADLINE (TENTATIVE) | UPDATE/ NOTE (IF ANY)
1 | In (Received): 16 scopes Hanoi 11 - 5 HCM | 1. Mr. Thang/ Mr. Nguyen 2. Ngan | Within next week (from 07-11/AUG)
2 | Out (Completed) 5 (1 Major - 4 Minor) Transfer to client: 0 Return unrepair: 0 | Mr. Thang/ Mr. Nguyen | DONE
3 | Waiting confirm: Recheck with Dealer/ Client about status: Confirmed to repair or Rejected Scope (HN: 63, HCM: 13) | Mr. Duc Tran | Within next week (from 07-11/AUG)
4 | Waiting for part: 12 | Mr. Thang/ Mr. Nguyen | Within next week (from 07-11/AUG)
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Completed job & Job assignment
Job completed (HCMC)
NO | Customer | Model | SN | Receive | Type | PIC | Nguyen | Hoang | Thong | Note
1 | Hoa Vang District General Hospital | EG-250WR5 | 1G202K323 | 2023-07-31 | Inspection | Thong |  |  | Inspection
2 | Vinh Duc General Hospital | EC-530WL3 | 5C643K343 | 2023-08-03 | Inspection | Thong |  |  | Inspection
3 | Thien Hanh Hospital | EG-530NW | 1G366K152 | 2023-08-03 | Inspection | Thong |  |  | Inspection
4 | Thien Hanh Hospital | EC-720R/I | 1C741K168 | 2023-08-03 | Inspection | Thong |  |  | Inspection
5 | Kon Tum Provincial General Hospital | EG-530WR | 4G361K372 | 2023-07-31 | Inspection | Thong |  |  | Inspection
6 | Kon Tum Provincial General Hospital | EC-530WL3 | 2C643K264 | 2023-07-31 | Inspection | Thong |  |  | Inspection
7 | VIET MY GENERAL CLINIC | EG-250WR5 | 1G202K621 |  | Major | Hoang |  | Major
8 | HECI Center | EG-760R | 3G402K143 | 2023-05-22 17:15 | Minor | Thong |  |  | Minor
9 | HECI Center | EG-760Z | 2G403K048 | 2023-05-22 16:53 | Minor | Thong |  |  | Minor | 2023-08-04
Job assignment (HCMC)
NO | Customer | Model | SN | Receive | Type | PIC | Nguyen | Hoang | Thong | Deadline
1 | 91 clinic | EG-760Z | 2G403K047 |  | Major | Thong |  |  | Major | 2023-08-10
2 | FUJIFILM Vietnam Co., Ltd. | EG-760R | 2G402K099 |  | Minor | Nguyen | Minor |  |  | 2023-08-10
Job completed (Ha Noi)
NO | Customer | Model | SN | Receive | Type | PIC | Thang | Hoan | Minh
1 | Re-Inspect 17 scope Bach Mai |  |  |  | Inspection | Minh + Hoan |  | Inspection | Inspection
2 | Hanoi Medical University Hospital | VP-4450HD | 3V567K036 | 2023-07-27 | Inspection | Minh |  |  | Inspection
3 | Tuyen Quang General Hospital | EC-201WI | RC328A025 | 2023-07-28 | Inspection | Minh |  |  | Inspection
4 | Tuyen Quang General Hospital | EC-530WL3 | 1C643K926 | 2023-07-28 | Inspection | Hoan |  | Inspection
5 | FTYO - Loaner Asset | EC-600WL | 1C692K141 | 2023-07-31 | Inspection | Minh |  |  | Inspection
6 | FUJIFILM Vietnam Co., Ltd. | EG-600WR | 1G391K315 | 2023-07-31 | Inspection | Minh |  |  | Inspection
7 | Promed | EG-760R | MG402K061 |  | Inspection | Thang | Inspection
8 | Promed | EC-760RVL | 9C729K018 |  | Inspection | Thang | Inspection
9 | Vietnam-Sweden Uong Bi Hospital | EG-530FP | 2G374K400 |  | Major | Hoan |  | Major
10 | Bac Giang Hospital | EG 530WR | 2G361K552 |  | Major | Minh |  |  | Major
11 | Hung Cuong Hospital-Hiep Hoa- Bac Giang | EG-530WR | JG361K231 | 2023-07-27 | Minor | Hoan |  | Minor
12 | National Lung Hospital | EB-530T | 1B084K400 | 2023-07-31 | Minor | Thang | Minor
13 | Thai Binh Hospital | EG-530WR | LG361K352 |  | Minor | Thang | Minor
14 | DONG HUNG HOSPITAL | EB-530S | 2B083K071 |  | Minor | Minh |  |  | Minor
15 | Friendship Hospital | VP-4450HD | 1V567K516 |  | Minor | Hoan |  | Minor
Job assignment (Ha Noi)
NO | Customer | Model | SN | Receive | Type | PIC | Thang | Hoan | MInh | Deadline
1 | Bac Giang Hospital | EG-600WR | 9G391K076 |  | Inspection | Thang | Inspection |  |  | 2023-08-10
2 | Phu Tho General Hospital | EG-530WR | JG361K553 |  | Inspection | Thang | Inspection |  |  | 2023-08-10
3 | Phu Tho General Hospital | EC-530WL3 | KC643K011 |  | Inspection | Minh |  |  | Inspection | 2023-08-10
4 | Phu Tho General Hospital | EC-530WL3 | JC643K007 |  | Inspection | Hoan |  | Inspection |  | 2023-08-10
5 | Thai Binh city general hospital | EG-530WR | LG361K344 |  | Inspection | Thang | Inspection |  |  | 2023-08-10
6 | Thai Binh Hospital | EC-530WL3 | KC643K088 |  | Inspection | Minh |  |  | Inspection | 2023-08-10
7 | Thai Binh Hospital | EC-530WL3 | KC643K248 |  | Major | Minh |  |  | Major | 2023-08-10
8 | Hai Duong Tuberculosis Hospital | EB-530T | 1B084K198 |  | Major | Hoan |  | Major |  | 2023-08-10
9 | 103 Military Hospital | VP-4450HD | 2V567K995 |  | Minor | Hoan |  | Minor |  | 2023-08-10