## Sheet1
| No | rma | cus_type | customer | dealer | location | installed_date | model | sn | scope_type | model2 | wty_end_date | receive | inspection | report_id | repair_size | issue | price | quotation | confirmation | stock_po | part_order_date | part_received_date | apas_no | apas_approved_date | start_repair | QC | return | link | pic | status | note | exfm_status | exfm_info | approval | repair_user | update_time | update_user | TAT_receive | TAT_PO | TAT_PART
0 | 1 | FMSV2023020019 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2019-12-04 00:00:00 | EC-760ZP-V/M | 2C730K027 | Colono | 760 | 2020-12-04 00:00:00 | 2023-02-08 00:00:00 | 2023-02-13 17:33:19 | 2302022TR | Major | BSA, FCT | 1241 | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023020019 | Thang | waiting for part | #PO109 | Inspection | Parts on Order |  |  | 2023-06-06 11:26:47.886000 | FFAP0066
1 | 2 | FMSV2023020022 | FF asset | FTYO - Loaner Asset |  | Hanoi | 2018-05-11 00:00:00 | EC-760ZP-V/M | 2C730K032 | Colono | 760 | 2019-05-11 00:00:00 | 2023-02-08 00:00:00 | 2023-02-14 12:09:53 | 2302023TR | Major | LGB, BSA, FSB | 2559 | FOC | [9 empty] | FTYO - Loaner Asset\FMSV2023020022 | FFAP0070 | waiting for part | #PO109 | Inspection | Parts on Order |  |  | 2023-06-06 11:25:51.529000 | FFAP0066
2 | 3 | FMSV2023020034 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2017-01-09 00:00:00 | EC-760R-V/I | 1C728K180 | Colono | 760 | 2018-01-09 00:00:00 | 2023-02-16 00:00:00 | 2023-02-23 00:00:00 | GDKT-2302022 | Major | AWT | 620 | 2023-03-22 00:00:00 | [9 empty] | Hoang Long Clinic\FMSV2023020034 | FFAP0062 | prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-30 15:36:27.579000 | thang
3 | 4 | FMSV2023020050 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2016-06-06 00:00:00 | EC-600WI | 1C692K487 | Colono | 600 | 2017-06-06 00:00:00 | 2023-02-21 00:00:00 | 2023-02-21 18:57:08 | 2302025TR | Minor | DWA | 8 | 2023-02-27 00:00:00 | 2023-02-27 00:00:00 | [8 empty] | Hanoi Medical University\FMSV2023020050 (FOC) | Thang | waiting for part | Confirmed: 27-Feb. | Parts Selection | Waiting for Parts |  |  | 2023-05-29 11:56:38.464000 | thongle
4 | 5 | FMSV2023020067 | Government | Hanoi Medical University Hospital |  | Hanoi | 2016-05-18 00:00:00 | VP-4450HD | 2V567K684 | Processor | 4450 | 2017-05-18 00:00:00 | 2023-02-28 17:07:16 | 2023-03-02 12:18:44 | GDKT-2303033 | Other | PCB | 11144 | 2023-03-15 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023020067 | FFAP0062 | LP/waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Waiting for Parts |  |  | 2023-07-11 10:55:22.985000 | thongle
5 | 6 | FMSV2023030008 | Government | Dong Thap Lung Hospital |  | HCM | 2009-05-05 00:00:00 | EB-530H | 3B087A006 | Broncho | 530 | 2010-05-05 00:00:00 | 2023-03-07 00:00:00 | 2023-03-07 17:31:23 | GDKT-2303037 | Major | ISA, FSB | 10777 | 2023-03-14 00:00:00 | [9 empty] | Dong Thap Lung Hospital\FMSV2023030008 |  | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:07:18.258000 | thongle
6 | 7 | FMSV2023030009 | Government | Dong Thap Lung Hospital |  | HCM | 2009-05-05 00:00:00 | EB-530T | 3B063A049 | Broncho | 530 | 2010-05-05 00:00:00 | 2023-03-07 00:00:00 | 2023-03-07 18:11:18 | GDKT-2303038 | Major | LGB, FSB, CAP | 9168 | 2023-03-14 00:00:00 | [9 empty] | Dong Thap Lung Hospital\FMSV2023030009 |  | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:07:34.504000 | thongle
7 | 8 | FMSV2023030032 | Private | ITO DONG NAI | ETC | HCM | 2018-12-31 00:00:00 | EPX-2500(230V) | 2V564K581 | Processor | 2500 | 2019-12-31 00:00:00 | 2023-03-20 00:00:00 | 2023-03-20 16:36:35 | GDKT-2303044 | Other | CN | 1415 | 2023-03-23 00:00:00 | [9 empty] | ITO Dong Nai\FMSV2023030032 | Hoang | LP/Waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-05-29 12:09:54.647000 | thongle
8 | 9 | FMSV2023030040 | Government | Viet Duc Hospital |  | HCM | 2017-12-11 00:00:00 | EC-760R-V/I | 1C728K450 | Colono | 760 | 2018-12-11 00:00:00 | 2023-03-21 00:00:00 | 2023-03-23 10:52:53 | GDKT-2303048 | Major | FSB, PCB | 2075 | 2023-03-30 00:00:00 | [9 empty] | Viet Duc Hospital\FMSV2023030040 | Nguyen | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:10:48.426000 | thongle
9 | 10 | FMSV2023030041 | Government | Hue University of Medicine and Pharmacy - Ginec | ETC | HCM | 2013-11-11 00:00:00 | EG-530WR | 4G361A481 | Gastro | 530 |  | 2023-03-23 00:00:00 | 2023-03-23 17:55:56 | GDKT-2303049 | Major | BSA, OSA | 1170 | 2023-04-14 00:00:00 | [9 empty] | Hue University of Medicine and Pharmacy - Ginec FMSV00043\FMSV2023030041 | thongle | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:11:11.637000 | thongle
10 | 11 | FMSV2023030060 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2017-02-08 00:00:00 | VP-7000 | 2V644K028 | Processor | 7000 | 2018-02-08 00:00:00 | 2023-03-23 19:41:03 | 2023-03-31 12:26:02 | GDKT-2304060 | Other | PCB | 5495 | 2023-04-14 00:00:00 | [9 empty] | Hoang Long Clinic\FMSV2023030060 | FFAP0062 | LP/prepairing quotation | SPR Project | Inspection | Waiting for Parts |  |  | 2023-06-26 13:12:00.505000 | thang
11 | 12 | FMSV2023030069 | Government | Thong Nhat Hospital | Trang Thi | HCM | 2019-12-24 00:00:00 | EC-720R/I | 1C741K218 | Colono | 720 | 2020-12-24 00:00:00 | 2023-03-28 00:00:00 | 2023-03-28 11:15:38 | GDKT-2303053 | Major | CHA, BSA, FSB, LGB | 4875 | 2023-03-29 00:00:00 | [9 empty] | Thong Nhat Hospital\FMSV2023030069 | Thong | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:22:25.187000 | thongle
12 | 13 | FMSV2023030073 | Private | No. 91 Endoscopy-Gastrointestinal-GI Scaning Test Clinic | ETC | HCM | 2018-09-01 00:00:00 | EC-760ZP-V/M | 2C730K036 | Colono | 760 | 2019-09-01 00:00:00 | 2023-03-29 11:40:10 | 2023-03-29 11:52:12 | GDKT-2303055 | Major |  | 1920 | 2023-03-29 00:00:00 | 2023-07-19 00:00:00 | [5 empty] | 2023-07-19 00:00:00 | 2023-07-19 00:00:00 | 2023-07-19 00:00:00 | Endoscopy No. 91 Clinic\FMSV2023030073 |  | Completed repair | End: 19-Jul.Confirmed: 19-Jul | Authorization |  | Approval |  | 2023-07-19 09:55:14.438000 | Nguyen
13 | 14 | FMSV2023030075 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi |  | EC-530WI | 1C603K041 | Colono | 530 | 2020-03-20 00:00:00 | 2023-03-30 00:00:00 | 2023-04-04 18:33:19 | 2304047TR | Major | CHA, FCT, BSA | 2490 | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023030075 | FFAP0070 | waiting for part | #PO109 | Inspection | Parts on Order |  |  | 2023-06-06 11:15:31.114000 | FFAP0066
14 | 15 | FMSV2023030079 | Private | DONG TRIEU GENERAL HOSPITAL |  | Hanoi | 2016-10-28 00:00:00 | VP-4450HD | 2V567K740 | Processor | 4450 | 2017-10-28 00:00:00 | 2023-03-30 00:00:00 | 2023-04-04 18:05:31 | GDKT-2304064 | Other | PCB | 11144 | 2023-04-11 00:00:00 | [9 empty] | Dong Trieu General Hospital\FMSV2023030079 | Hoanle | LP/waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-05-29 12:25:55.676000 | thongle
15 | 16 | FMSV2023040002 | Private | Dai Duong Tien Hai General Clinic |  | Hanoi | 2021-10-28 00:00:00 | EC-600ZW/L | 2C695K023 | Colono | 600 | 2022-10-28 00:00:00 | 2023-04-03 16:52:24 | 2023-04-11 12:54:41 | GDKT-2304066 | Major | CHA | 10787 | 2023-04-14 00:00:00 | 2023-05-15 00:00:00 | [8 empty] | Dai Duong Tien Hai General Clinic\FMSV2023040002 | Thang | waiting for part | Confirmed: 15-May. #PO108 | Authorization | Parts on Order | Approval |  | 2023-07-24 15:45:28.210000 | thang
16 | 17 | FMSV2023040004 | FF asset | FTYO - Loaner Asset |  | Hanoi | 2014-07-15 00:00:00 | EN-580T | 1C675K021 | Entero Scope | 580 | 2015-07-16 00:00:00 | 2023-04-03 00:00:00 | 2023-04-11 13:22:41 | 2304053TR | Major | FCT, BSA | 907 | FOC | [9 empty] | FTYO - Loaner Asset\FMSV2023040004 | FFAP0070 | waiting for part | #PO109 | Inspection | Parts on Order |  |  | 2023-06-06 11:16:02.790000 | FFAP0066
17 | 18 | FMSV2023040010 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2020-06-12 00:00:00 | EG-600WR | 7G391K201 | Gastro | 600 | 2021-06-13 00:00:00 | 2023-04-04 00:00:00 | 2023-04-06 13:48:55 | GDKT-2304062 | Major | BSA, FCT, FSB, ISA, WGB | 3495 | 2023-04-11 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023040010 | Thang | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:29:02.343000 | thongle
18 | 19 | FMSV2023040017 | Private | Phu Tho General Hospital - Pediatric Center | Thanh An | Hanoi | 2019-03-12 00:00:00 | EG-530FP | 4G374K157 | Gastro | 530 | 2020-03-12 00:00:00 | 2023-04-05 00:00:00 | 2023-04-18 10:32:57 | GDKT-2304076 | Major | CHA, BSA, FSA, LPA | 6918 | 2023-04-05 00:00:00 | [9 empty] | Phu Tho General Hospital\FMSV2023040017 | FFAP0062 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:29:21.083000 | thongle
19 | 20 | FMSV2023040019 | private | Viet Tiep Friendship Hospital- Hai Phong |  | Hanoi | 2020-09-24 00:00:00 | EC-530WI3 | 5C642K125 | Colono | 530 | 2021-09-24 00:00:00 | 2023-04-06 00:00:00 | 2023-04-14 18:37:37 | GDKT-2304070 | Major | DEC, CHA, FSA, BSA | 6995 | 2023-04-20 00:00:00 | [9 empty] | Viet Tiep Friendship Hospital- Hai Phong\FMSV2023040019 | Thang | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:29:38.652000 | thongle
20 | 21 | FMSV2023040024 | Government | Vietnam – Cuba Donghoi Friendship Hospital | Promed | Hanoi | 2020-03-01 00:00:00 | EG-760R | 6G402K258 | Gastro | 760 | 2021-03-01 00:00:00 | 2023-04-11 00:00:00 | 2023-04-14 18:04:06 | GDKT-2304071 | Major | CHA, FCT, FSB | 6238 | 2023-04-28 00:00:00 | [9 empty] | Vietnam – Cuba Donghoi Friendship Hospital\FMSV2023040024 | FFAP0070 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:31:12.330000 | thongle
21 | 22 | FMSV2023040025 | Government | Vietnam – Cuba Donghoi Friendship Hospital | Promed | Hanoi | 2020-03-01 00:00:00 | EC-760R-V/I | 5C728K054 | Colono | 760 | 2021-03-01 00:00:00 | 2023-04-11 00:00:00 | 2023-04-14 19:12:18 | GDKT-2304072 | Major | FSA, CHA, DEC, FSB, LGB | 14180 | 2023-04-28 00:00:00 | [9 empty] | Vietnam – Cuba Donghoi Friendship Hospital\FMSV2023040025 | FFAP0070 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:31:27.140000 | thongle
22 | 23 | FMSV2023040038 | Government | 115 PEOPLE HOSPITAL | Trang Thi | HCM | 2017-01-11 00:00:00 | EC-600WI | 1C692K648 | Colono | 600 | 2018-01-11 00:00:00 | 2023-04-13 00:00:00 | 2023-04-13 16:22:06 | GDKT-2304067 | Major | BSA, DEC, FSA, SUT, VCA | 7081 | 2023-04-14 00:00:00 | [9 empty] | 115 People Hospital\FMSV2023040038 | thongle | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:38:08.568000 | thongle
23 | 24 | FMSV2023040040 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2023-01-01 00:00:00 | EG-760R | JG402K336 | Gastro | 760 | 2024-01-01 00:00:00 | 2023-04-13 18:39:15 | 2023-04-18 18:57:58 | FFVN-2304051TR | Major | FSB, BSA | 1340 | FOC | 2023-06-08 00:00:00 | [8 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023040040 | FFAP0070 | Under repair | Start: 19-Jul.#PO109 | Authorization | Parts on Order | Approval |  | 2023-07-19 15:36:27.563000 | FFAP0062
24 | 25 | FMSV2023040041 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2017-02-22 00:00:00 | XL-4450 | 3S094K410 | Processor | 4450 | 2018-02-22 00:00:00 | 2023-04-13 20:02:46 | 2023-04-18 18:07:57 | GDKT-2304075 | Other | IRS | 1241 | 2023-04-28 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023040041 | Hoanle | LP/waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:01:00.031000 | FFAP0104
25 | 26 | FMSV2023040043 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2019-03-28 00:00:00 | ED-580XT | 2D127K107 | Duo Scope | 580 | 2020-03-28 00:00:00 | 2023-04-14 00:00:00 | 2023-04-18 19:05:06 | FFVN-2304052TR | Major | BSA | 888 | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023040043 | FFAP0070 | waiting for part | PO#108 | Inspection | Parts on Order |  |  | 2023-06-05 10:51:50.550000 | FFAP0066
26 | 27 | FMSV2023040049 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2021-11-20 00:00:00 | EG-600WR | 8G391K423 | Gastro | 600 | 2022-11-20 00:00:00 | 2023-04-18 00:00:00 | 2023-04-27 20:01:13 | GDKT-2023040049 | Major | FSA, FSB, VCA, BSA, FCT | 5123 | 2023-06-14 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023040049 | Thang | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:46:18.694000 | thongle
27 | 28 | FMSV2023040060 | Government | Quang Ninh Obstetrics And Pediatrics Hospital |  | Hanoi | 2018-10-20 00:00:00 | ER-530S2 | 3Y196K006 | Broncho | 530 | 2019-10-20 00:00:00 | 2023-04-19 00:00:00 | 2023-04-25 16:49:56 | GDKT-2304078 | Major | RBS, ISA, BSA | 9371 | 2023-04-27 00:00:00 | [9 empty] | Quang Ninh Obstetrics And Pediatrics Hospital\FMSV2023040060 | Thang | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:47:03.301000 | thongle
28 | 29 | FMSV2023040063 | Government | K3 Hanoi National Cancer Hospital |  | Hanoi | 2017-11-24 00:00:00 | EG-760R | 1G402K679 | Gastro | 760 | 2018-11-24 00:00:00 | 2023-04-24 00:00:00 | 2023-04-26 16:52:45 | GDKT-2304080 | Major | OSA, BSA, FCT | 2615 | 2023-05-04 00:00:00 | [9 empty] | K3 Hanoi National Cancer Hospital\FMSV2023040063 | FFAP0070 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:48:24.509000 | thongle
29 | 30 | FMSV2023040064 | Government | K3 Hanoi National Cancer Hospital |  | Hanoi | 2017-11-24 00:00:00 | EC-760R-V/I | 1C728K447 | Colono | 760 | 2018-11-24 00:00:00 | 2023-04-24 00:00:00 | 2023-04-26 18:24:18 | GDKT-2304081 | Major | CHA, WJT, BSA | 14077 | 2023-05-04 00:00:00 | [9 empty] | K3 Hanoi National Cancer Hospital\FMSV2023040064 | FFAP0070 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:48:35.895000 | thongle
30 | 31 | FMSV2023040065 | Government | K3 Hanoi National Cancer Hospital |  | Hanoi | 2018-10-30 00:00:00 | EC-760R-V/I | 2C728K080 | Colono | 760 | 2019-10-30 00:00:00 | 2023-04-24 00:00:00 | 2023-04-25 13:05:59 | GDKT-2023040065 | Major | AWT, LGB, BSA, AWB | 4620 | 2023-05-08 00:00:00 | [9 empty] | K3 Hanoi National Cancer Hospital\FMSV2023040065 | FFAP0062 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:48:52.547000 | thongle
31 | 32 | FMSV2023040066 | Government | K3 Hanoi National Cancer Hospital |  | Hanoi | 2017-11-24 00:00:00 | EG-760R | 1G402K680 | Gastro | 760 | 2018-11-24 00:00:00 | 2023-04-24 00:00:00 | 2023-04-26 17:10:16 | GDKT-2304082 | Major | CHA, FCT, BSA, FSA | 9761 | 2023-04-28 00:00:00 | [9 empty] | K3 Hanoi National Cancer Hospital\FMSV2023040066 | FFAP0070 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 12:49:12.510000 | thongle
32 | 33 | FMSV2023040070 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2017-07-01 00:00:00 | EG-590WR | 2G348K408 | Gastro | 590 | 2018-07-01 00:00:00 | 2023-04-26 00:00:00 | 2023-05-18 00:00:00 | GDKT-2023040070 | Major | PCB, CHA |  | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023040070 | thongle | waiting approved |  | Inspection | Waiting for Parts |  |  | 2023-06-21 16:31:01.891000 | Nguyen
33 | 34 | FMSV2023040077 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2019-12-26 00:00:00 | EG-600WR | 7G391K085 | Gastro | 600 | 2020-12-26 00:00:00 | 2023-04-27 00:00:00 | 2023-04-27 18:01:53 | GDKT-2304084 | Major | FSA, FSB, BSA, FCT | 7592 | 2023-05-29 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023040077 | FFAP0062 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-06-16 19:01:32.297000 | thongle
34 | 35 | FMSV2023040090 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2021-08-06 00:00:00 | EG-600WR | 8G391K374 | Gastro | 600 | 2022-08-12 00:00:00 | 2023-04-27 00:00:00 | 2023-05-12 00:00:00 | GDKT-2023040090 | Major | VCA, FCT, BSA | 3320 | 2023-06-23 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023040090 | Minh | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Parts billing |  |  | 2023-06-12 11:23:03.635000 | thongle
35 | 36 | FMSV2023040091 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2021-11-20 00:00:00 | EG-600WR | 8G391K428 | Gastro | 600 | 2022-11-20 00:00:00 | 2023-04-27 00:00:00 | 2023-05-11 16:58:03 | GDKT-2023040091 | Major | DRY, FCT, FSB, BSA, VCA | 4413 | 2023-06-05 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023040091 | FFAP0062 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-06-08 17:39:14.259000 | thang
36 | 37 | FMSV2023040092 | Government | Bac Giang Hospital |  | Hanoi | 2015-12-08 00:00:00 | EC-530WL3 | 1C643K395 | Colono | 530 | 2016-12-07 00:00:00 | 2023-04-28 00:00:00 | 2023-05-08 19:18:14 | GDKT-2023040092 | Major | FSA, BSA, LGB, DEC, VCA, FSB | 6919 | 2023-05-09 00:00:00 | [9 empty] | Bac Giang Hospital\FMSV2023040092 | Thang | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 13:00:16.457000 | thongle
37 | 38 | FMSV2023050013 | Private | Thanh An- Ha Noi limited company | Trang Thi | Hanoi | 2018-10-23 00:00:00 | EG-760Z | 1G403K362 | Gastro | 760 | 2019-10-23 00:00:00 | 2023-05-08 00:00:00 | 2023-05-15 15:39:03 | GDKT-2023050013 | Major | LLA, FSA, BSA, FCT | 4760 | 2023-06-05 00:00:00 | [9 empty] | Thanh An- Ha Noi limited company\FMSV2023050013 | FFAP0070 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-06-08 17:39:24.128000 | thang
38 | 39 | FMSV2023050016 | Private | Thanh An- Ha Noi limited company | Trang Thi | Hanoi | 2019-06-18 00:00:00 | EG-760R | 2G402K098 | Gastro | 760 | 2020-06-18 00:00:00 | 2023-05-08 00:00:00 | 2023-05-15 16:02:10 | GDKT-2023050016 | Major | CHA, BSA, FSA | 8389 | 2023-06-05 00:00:00 | [9 empty] | Thanh An- Ha Noi limited company\FMSV2023050016 | FFAP0070 | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-06-08 17:39:35.025000 | thang
39 | 40 | FMSV2023050018 | Government | Dam Doi Hospital |  | HCM | 2015-08-06 00:00:00 | EG-250WR5 | SG202A469 | Gastro | 250 | 2016-08-05 00:00:00 | 2023-05-09 00:00:00 | 2023-05-09 15:38:25 | GDKT-2023050018 | Major | LGB, FSA, FSB, PCB | 4274 | 2023-05-10 00:00:00 | [9 empty] | Dam Doi hospital\FMSV2023040063 | Nguyen | waiting confirm | 2. dealer sending price to hospital | Inspection | Awating Contract billing |  |  | 2023-05-29 13:11:21.285000 | thongle
40 | 41 | FMSV2023050020 | Private | Thien Hanh Hospital | ETC | HCM | 2017-07-05 00:00:00 | VP-4450HD | 2V567K860 | Processor | 4450 | 2018-07-05 00:00:00 | 2023-05-10 00:00:00 | 2023-05-10 13:19:14 | GDKT-2023050020 | Other |  | 10336 | 2023-05-10 00:00:00 | [9 empty] | Thien Hanh hospital\FMSV2023050020 | thongle | LP/Transfer to sale team | RU: . Old Stt: LP/waiting confirm. | Inspection |  |  |  | 2023-05-29 13:12:30.473000 | thongle
41 | 42 | FMSV2023050021 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2019-08-25 00:00:00 | EC-590WL4 | 1C666K565 | Colono | 590 | 2020-08-25 00:00:00 | 2023-05-09 00:00:00 | 2023-05-09 00:00:00 | GDKT-2023050021 | Major | FSA, FSB, VCA, BSA, DWA | 5351 | 2023-05-09 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023050021 | Thang | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-05-29 13:13:06.859000 | thongle
42 | 43 | FMSV2023050023 | Government | Hai Duong Tuberculosis Hospital |  | Hanoi | 2016-05-13 00:00:00 | EB-530T | 1B084K198 | Broncho | 530 | 2017-05-13 00:00:00 | 2023-05-09 00:00:00 | 2023-05-16 17:48:50 | GDKT-2023050023 | Major | FSB, RBS | 1034 | 2023-06-05 00:00:00 | [9 empty] | Hai Duong Tuberculosis Hospital\FMSV2023050023 | FFAP0070 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-08 17:39:49.418000 | thang
43 | 44 | FMSV2023050024 | Private | Lam Hoa Private Hospital |  | Hanoi | 2020-03-25 00:00:00 | EG-250WR5 | 3G202K117 | Gastro | 250 | 2021-03-25 00:00:00 | 2023-05-09 00:00:00 | 2023-05-16 18:20:48 | GDKT-2023050024 | Major | CHA | 4315 | 2023-06-05 00:00:00 | [9 empty] | Lam Hoa Private Hospital\FMSV2023050024 | FFAP0070 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-06 13:13:12.910000 | FFAP0066
44 | 45 | FMSV2023050025 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2017-01-09 00:00:00 | EG-760R | 1G402K303 | Gastro | 760 |  | 2023-05-10 12:39:50 | 2023-05-17 12:42:16 | GDKT-2023050025 | Major | BSA, FCT, FSA | 2840 | 2023-06-05 00:00:00 | [9 empty] | Hoang Long Clinic\FMSV2023050025 | FFAP0070 | prepairing quotation | SPR Project | Inspection | Waiting for Parts |  |  | 2023-06-23 18:44:53.581000 | FFAP0066
45 | 46 | FMSV2023050033 | Private | Phu Tho General Hospital - Pediatric Center | Thanh An | Hanoi | 2019-03-12 00:00:00 | EG-530FP | 4G374K154 | Gastro | 530 | 2020-03-12 00:00:00 | 2023-05-12 00:00:00 | 2023-05-23 00:00:00 | GDKT-2023050033 | Major | FCT, CHA, BSA, FSA | 6457 | 2023-06-09 00:00:00 | [9 empty] | Phu Tho General Hospital - Pediatric Center\FMSV2023050033 | FFAP0070 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-23 19:33:02.837000 | FFAP0066
46 | 47 | FMSV2023050034 | Government | Thai Nguyen General Hospital | Promed | Hanoi | 2019-02-27 00:00:00 | EC-250WL5 | 3C309K012 | Colono | 250 | 2020-02-27 00:00:00 | 2023-05-22 00:00:00 | 2023-05-22 13:36:34 | GDKT-2023050034 | Minor | DWA, DTA | 235 | 2023-06-05 00:00:00 | [9 empty] | Thai Nguyen General Hospital\FMSV2023050034 | FFAP0070 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-08 17:40:26.596000 | thang
47 | 48 | FMSV2023050035 | Government | Thai Nguyen General Hospital | Promed | Hanoi | 2019-01-29 00:00:00 | EC-250WL5 | 3c309k028 | Colono | 250 | 2020-01-29 00:00:00 | 2023-05-08 00:00:00 | 2023-05-22 15:51:12 | GDKT-2023050035 | Major | PCB, BSA | 2342 | 2023-06-05 00:00:00 | [9 empty] | Thai Nguyen General Hospital\FMSV2023050035 | Thang | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-08 17:40:39.843000 | thang
48 | 49 | FMSV2023050038 | Private | ETC Company | ETC | HCM | 2018-06-12 00:00:00 | EC-530WL3 | 2C643K211 | Colono | 530 | 2019-06-12 00:00:00 | 2023-05-22 00:00:00 | 2023-05-22 17:35:11 | GDKT-2023050038 | Major | DRY, FSA, BSA, DEC | 3103 | 2023-05-23 00:00:00 | [9 empty] | ETC Company\FMSV2023050038 | thongle | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | PO Received |  |  | 2023-05-30 12:03:27.698000 | Nguyen
49 | 50 | FMSV2023050041 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2022-11-03 00:00:00 | EG-760Z | 8G403K090 | Gastro | 760 | 2023-11-03 00:00:00 | 2023-05-22 00:00:00 | 2023-05-22 17:44:37 | GDKT-2023050041 | Major | FSB, DRY | 685 | FOC | 2023-06-08 00:00:00 | [8 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023050041 | thongle | waiting for part | #PO109 | Inspection | Parts on Order |  |  | 2023-06-06 11:22:29.027000 | FFAP0066
50 | 51 | FMSV2023050042 | Private | Hoan My Da Nang Hospital | ETC | HCM | 2018-08-03 00:00:00 | VP-4450HD | 2V567K886 | Processor | 4450 | 2019-08-03 00:00:00 | 2023-05-10 13:13:05 | 2023-05-29 11:07:35 | GDKT-2023050042 | Other | PCB | 10270 | 2023-05-29 00:00:00 | [9 empty] | Hoan My Da Nang Hospital\FMSV2023050042 | thongle | LP/waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-05-29 13:11:59.272000 | FFAP0066
51 | 52 | FMSV2023050045L | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2013-07-04 00:00:00 | EC-530WI | 4C591A001 | Colono | 530 | 2014-07-04 00:00:00 | 2023-06-13 00:00:00 | 2023-07-04 00:00:00 | GDKT-2023050045L |  | FSB, DRY |  | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023050045L | thongle | waiting approved |  | Inspection | Awating Internal Approval |  |  | 2023-07-04 17:04:40.490000 | thongle
52 | 53 | FMSV2023050047 | Government | Thai Binh Hospital | Promed | Hanoi | 2017-04-05 00:00:00 | EB-530S | 1B083K279 | Broncho | 530 | 2018-04-05 00:00:00 | 2023-05-10 00:00:00 | 2023-05-24 18:33:23 | GDKT-2023050047 | Major | CHA, FCT | 7203 | 2023-06-05 00:00:00 | [9 empty] | Thai Binh Hospital\FMSV2023050047 | FFAP0062 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-06 13:13:51.883000 | FFAP0066
53 | 54 | FMSV2023050048 | Government | Thai Binh Hospital | Promed | Hanoi | 2017-03-11 00:00:00 | EB-530S | 1B083K278 | Broncho | 530 | 2018-03-11 00:00:00 | 2023-05-11 00:00:00 | 2023-05-25 12:10:27 | GDKT-2023050048 | Major | CHA, FCT, PCB | 7203 | 2023-06-07 00:00:00 | [9 empty] | Thai Binh Hospital\FMSV2023050048 | FFAP0062 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-07 10:57:23.677000 | FFAP0066
54 | 55 | FMSV2023050049 | Government | Bai Chay Hospital | MDC | Hanoi | 2015-11-19 00:00:00 | EC-600WI | 1C692K270 | Colono | 600 | 2016-11-19 00:00:00 | 2023-05-12 00:00:00 | 2023-05-25 19:30:19 | GDKT-2023050049 | Major | CHA, BSA, FSB | 9489 | 2023-06-05 00:00:00 | [9 empty] | Bai Chay Hospital\FMSV2023050049 | Thang | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-08 17:41:08.996000 | thang
55 | 56 | FMSV2023050053 | Government | Bac Giang Hospital |  | Hanoi | 2016-11-28 00:00:00 | EC-530WL3 | 1C643K899 | Colono | 530 | 2017-11-28 00:00:00 | 2023-05-12 00:00:00 | 2023-05-26 15:38:49 | GDKT-2023050053 | Major | CHA, FSB, VCA, BSA | 10257 | 2023-06-07 00:00:00 | [9 empty] | Bac Giang Hospital\FMSV2023050053 | FFAP0062 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-07 11:10:03.662000 | FFAP0066
56 | 57 | FMSV2023050062 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2017-05-15 00:00:00 | EG-600WR | 2G391K780 | Gastro | 600 | 2018-05-15 00:00:00 | 2023-05-29 00:00:00 | 2023-05-30 10:46:11 | GDKT-2023050062 | Major | BSA, FCT | 2163 | 2023-06-05 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023050062 | FFAP0070 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-16 19:03:22.573000 | thongle
57 | 58 | FMSV2023050064 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2019-12-26 00:00:00 | EC-600WI | 5C692K030 | Colono | 600 | 2020-12-26 00:00:00 | 2023-05-25 11:40:04 | 2023-05-30 09:50:49 | TR-2023050064 | Minor | DWA |  | FOC | [9 empty] | Hanoi Medical University\FMSV2023050064 (FOC) |  | waiting approved |  | Parts Selection | Awating Parts billing |  |  | 2023-06-27 10:56:19.919000 | thang
58 | 59 | FMSV2023050071 | Government | Bai Chay Hospital | MDC | Hanoi | 2016-11-22 00:00:00 | EG-600WR | 2G391K484 | Gastro | 600 | 2018-01-13 00:00:00 | 2023-05-29 00:00:00 | 2023-06-02 19:44:58 | GDKT-2023050071 | Major | FSA, BSA, FCT, FSB, VCA | 5653 | 2023-06-05 00:00:00 | 2023-06-12 00:00:00 | [8 empty] | Bai Chay Hospital\FMSV2023050071 | Thang | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-08 17:41:20.153000 | thang
59 | 60 | FMSV2023050072 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2015-07-08 00:00:00 | EG-600WR | 1G391K564 | Gastro | 600 | 2016-07-07 00:00:00 | 2023-05-29 18:47:44 | 2023-06-02 13:29:45 | TR-2023050072 | Major | DRY, BSA, FCT, DEC |  | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023050072 | FFAP0070 | waiting approved |  | Inspection | Awating Parts billing |  |  | 2023-06-26 18:02:17.706000 | thang
60 | 61 | FMSV2023050075 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2021-02-23 00:00:00 | ED-580XT | 3D127K339 | Duo Scope | 580 | 2022-03-01 00:00:00 | 2023-05-29 19:03:53 | 2023-06-01 13:17:05 | GDKT-2023050075 | Major | BSA | 1368 | 2023-06-05 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023050075 | FFAP0062 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-07-12 13:50:33.295000 | FFAP0104
61 | 62 | FMSV2023050076 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2021-11-20 00:00:00 | EG-600WR | 8G391K430 | Gastro | 600 | 2022-11-20 00:00:00 | 2023-05-29 00:00:00 | 2023-06-08 00:00:00 | GDKT-2023050076 | Major | DRY, FSB, FCT, VCA, BSA | 4463 | 2023-06-09 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023050076 | FFAP0062 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-23 19:29:01.322000 | FFAP0066
62 | 63 | FMSV2023050078 | Government | Thai Binh Hospital | Promed | Hanoi | 2023-03-21 00:00:00 | EG-530WR | LG361K357 | Gastro | 530 | 2024-03-21 00:00:00 | 2023-05-30 00:00:00 | 2023-06-01 19:14:12 | FFVN-2306019 | Minor | VCA |  | WARRANTY | [9 empty] | Thai Binh Hospital\FMSV2023050078 | Thang | waiting for part | Approved: 12-Jun-23. Warranty Parts. | Inspection | Waiting for Parts |  |  | 2023-06-15 18:49:50.196000 | thongle
63 | 64 | FMSV2023050079 | Government | Thai Binh Hospital | Promed | Hanoi | 2023-03-21 00:00:00 | EC-530WL3 | KC643K248 | Colono | 530 | 2024-03-21 00:00:00 | 2023-05-30 00:00:00 | 2023-06-01 13:29:45 | FFVN-2306017 | Major | WJT, CHA, BSA |  | WARRANTY | [9 empty] | Thai Binh Hospital\FMSV2023050079 | jasper | waiting for part | Approved: 05-Jun-23. Warranty Parts. | Inspection | Waiting for Parts |  |  | 2023-06-15 18:50:10.338000 | thongle
64 | 65 | FMSV2023050081 | FF asset | HCAP asset |  | Hanoi | 2012-05-14 00:00:00 | XL-4450 | 1S094A412 | Processor | 4450 | 2013-05-13 00:00:00 | 2023-05-31 17:01:21 | 2023-06-01 10:51:21 | TR-2023050081 | Other | POW, IRS, FUS | [11 empty] | FFAP asset\FMSV2023050081 | Thang | LP/waiting approved |  | Inspection | Awating Parts billing |  |  | 2023-06-26 18:04:02.742000 | thang
65 | 66 | FMSV2023050082 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2019-06-04 00:00:00 | EC-530WL3 | 3C643K019 | Colono | 530 | 2020-06-04 00:00:00 | 2023-05-31 00:00:00 | 2023-06-02 17:55:52 |  | Minor | DWA | [12 empty] | FFAP0062 | waiting approved |  | Parts Selection |  |  |  | 2023-06-02 18:02:09.054000 | FFAP0062
66 | 67 | FMSV2023060003 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2017-08-30 00:00:00 | EG-250WR5 | 2G202K058 | Gastro | 250 | 2018-08-30 00:00:00 | 2023-06-13 13:04:51 | 2023-06-13 13:07:12 | GDKT-2023060003 | Major |  |  | FOC | [8 empty] | 2023-07-20 00:00:00 | FUJIFILM Vietnam Co., Ltd\FMSV2023060003 |  | Completed repair | End: 19-Jul.Part OK: 16-Jun. Approved: 14-Jun-23. (Write off) | Authorization |  | Approval |  | 2023-07-19 17:02:33.284000 | Nguyen
67 | 68 | FMSV2023060011 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2020-12-24 00:00:00 | EG-600WR | 8G391K041 | Gastro | 600 | 2021-12-24 00:00:00 | 2023-06-05 00:00:00 | 2023-06-05 00:00:00 | GDKT-2023060011 | Major | CHA, FCT, BSA, OSA | 8142 | 2023-06-09 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023060011 | FFAP0062 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-23 19:30:08.385000 | FFAP0066
68 | 69 | FMSV2023060016 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2016-06-06 00:00:00 | XL-4450 | 2S094K543 | Processor | 4450 | 2017-06-06 00:00:00 | 2023-06-06 15:45:24 | 2023-06-06 19:40:18 | GDKT-2023060016 | Other | IRS |  | 2023-06-12 00:00:00 | 2023-06-12 00:00:00 | [8 empty] | Hanoi Medical University\FMSV2023060016 | FFAP0062 | LP/prepairing quotation | Start: 19-Jun End: 23-Jun. Part OK: 12-Jun. Confirmed: 12-Jun. | Inspection | Awating Contract billing |  |  | 2023-06-23 19:31:46.497000 | FFAP0066
69 | 70 | FMSV2023060018 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2019-03-20 00:00:00 | EG-530WR | 2G361K546 | Gastro | 530 | 2020-03-20 00:00:00 | 2023-06-08 00:00:00 | 2023-06-08 10:45:43 | GDKT-2023060018 | Major | ISA, PCB, VCA | 4104 | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023060018 | Nguyen | waiting for part | #PO109 | Inspection | Awating Parts billing |  |  | 2023-06-08 12:40:03.013000 | Nguyen
70 | 71 | FMSV2023060022 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2018-04-20 00:00:00 | EC-760ZP-V/M | 2C730K019 | Colono | 760 | 2019-04-20 00:00:00 | 2023-06-08 12:11:56 | 2023-06-08 12:14:28 | GDKT-2023060022 | Minor |  | 654 | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023060022 | hoang | Completed repair | End: 17-Jul.#PO109 | Repair |  | Approval | hoang | 2023-07-17 18:18:06.908000 | hoang
71 | 72 | FMSV2023060024 | Private | HECI Center | GMS | HCM | 2018-08-13 00:00:00 | EG-760R | 3G402K143 | Gastro | 760 | 2021-08-13 00:00:00 | 2023-06-09 00:00:00 | 2023-06-09 16:15:33 | GDKT-2023060024 | Minor | ANGL | 1403 | 2023-06-09 00:00:00 | 2023-06-16 00:00:00 | [8 empty] | HECI Center\FMSV2023060024 | thongle | waiting for part | Confirmed: 16-Jun. 1. Less than 4 weeks after giving the quotation | Inspection | PO Received |  |  | 2023-06-16 19:04:54.018000 | thongle
72 | 73 | FMSV2023060027 | FF asset | FTYO - Loaner Asset |  | HCM | 2019-02-12 00:00:00 | ED-530XT8 | 3D103L050 | Duo Scope | 530 |  | 2023-06-27 00:00:00 | 2023-06-27 00:00:00 | GDKT-2023060027 | Major | FCT | 270 | FOC | [9 empty] | \FUJIFILM Vietnam Co., Ltd\FMSV2023060027 | thongle | waiting approved |  | Inspection | Waiting for Next Process Available |  |  | 2023-06-27 17:41:00.871000 | thongle
73 | 74 | FMSV2023060038 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2021-11-20 00:00:00 | EG-600WR | 8G391K429 | Gastro | 600 | 2022-11-20 00:00:00 | 2023-06-19 00:00:00 | 2023-06-22 00:00:00 |  | Major | OSA, CHA, FSA, BSA | 11795 | 2023-06-28 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023060038 | FFAP0070 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-29 12:14:44.767000 | FFAP0104
74 | 75 | FMSV2023060039 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2014-10-12 00:00:00 | EC-600WI | 1C692K176 | Colono | 600 | 2015-10-11 00:00:00 | 2023-06-19 00:00:00 | 2023-06-20 00:00:00 | TR-2023060039 | Major | AWT |  | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023060039 | Thang | waiting approved |  | Inspection |  |  |  | 2023-06-20 17:21:28.233000 | thang
75 | 76 | FMSV2023060040 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2021-11-20 00:00:00 | EG-600WR | 8G391K431 | Gastro | 600 | 2022-11-20 00:00:00 | 2023-06-19 00:00:00 | 2023-06-22 00:00:00 |  | Major | BSA, CHA, VCA, FSB | 10819 | 2023-06-28 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023060040 | FFAP0070 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-29 12:13:55.029000 | FFAP0104
76 | 77 | FMSV2023060041 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2017-01-09 00:00:00 | EC-760R-V/I | 1C728K176 | Colono | 760 | 2018-01-09 00:00:00 | 2023-06-19 16:17:03 | 2023-06-20 12:08:31 | GDKT-2023060041 | Major | WJT, CHA, BSA | [11 empty] | Hoang Long Clinic\FMSV2023060041 | FFAP0070 | prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-26 12:18:04.623000 | thongle
77 | 78 | FMSV2023060042 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2018-12-31 00:00:00 | EG-760R | 2G402K285 | Gastro | 760 | 2019-12-31 00:00:00 | 2023-06-19 16:20:36 | 2023-06-20 12:30:59 | GDKT-2023060042 | Major | FCT, AWT | [11 empty] | Hoang Long Clinic\FMSV2023060042 | FFAP0070 | prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-26 12:18:14.304000 | thongle
78 | 79 | FMSV2023060043 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2016-10-30 00:00:00 | EC-600WI | 1C692K643 | Colono | 600 | 2017-10-30 00:00:00 | 2023-06-19 16:21:44 | 2023-06-20 13:27:39 | GDKT-2023060043 | Major | SW, FSA, BSA | [11 empty] | Hoang Long Clinic\FMSV2023060043 | FFAP0070 | prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-26 12:19:13.885000 | thongle
79 | 80 | FMSV2023060044 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2017-02-08 00:00:00 | EG-760R | 1G402K304 | Gastro | 760 | 2018-02-08 00:00:00 | 2023-06-19 16:23:02 | 2023-06-20 11:41:57 | GDKT-2023060044 | Major | BSA, FCT, FSA | [11 empty] | Hoang Long Clinic\FMSV2023060044 | FFAP0070 | prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-26 12:19:24.659000 | thongle
80 | 81 | FMSV2023060045 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2015-07-08 00:00:00 | EG-600WR | 1G391K563 | Gastro | 600 | 2016-07-07 00:00:00 | 2023-06-19 16:23:54 | 2023-06-20 12:31:04 | GDKT-2023060045 | Major | FCT | [11 empty] | Hoang Long Clinic\FMSV2023060045 | FFAP0062 | prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-26 12:19:31.825000 | thongle
81 | 82 | FMSV2023060046 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2016-02-24 00:00:00 | EG-600WR | 1G391K985 | Gastro | 600 | 2017-02-24 00:00:00 | 2023-06-19 16:24:49 | 2023-06-20 17:46:07 | GDKT-2023060046 | Major | FCT | [11 empty] | Hoang Long Clinic\FMSV2023060046 | FFAP0062 | prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-26 12:20:15.627000 | thongle
82 | 83 | FMSV2023060047 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2017-02-08 00:00:00 | EG-760Z | 1G403K110 | Gastro | 760 | 2018-02-08 00:00:00 | 2023-06-19 16:25:50 | 2023-06-20 12:59:28 | GDKT-2023060047 | Minor | PCB | [11 empty] | Hoang Long Clinic\FMSV2023060047 | FFAP0070 | prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-26 13:13:24.823000 | thang
83 | 84 | FMSV2023060048 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2017-01-09 00:00:00 | EC-760R-V/I | 1C728K177 | Colono | 760 | 2018-01-09 00:00:00 | 2023-06-19 16:26:45 | 2023-06-20 10:45:29 | GDKT-2023060048 | Major | AWT, BSA, FCT, WGA | [11 empty] | Hoang Long Clinic\FMSV2023060048 | FFAP0062 | prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-26 12:20:41.041000 | thongle
84 | 85 | FMSV2023060053 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2019-01-01 00:00:00 | EG-600WR | 4G391K120 | Gastro | 600 | 2020-01-01 00:00:00 | 2023-06-20 00:00:00 | 2023-06-29 00:00:00 | GDKT-2023060053 | Major | BSA, FCT | 2137 | 2023-06-28 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023060053 | FFAP0104 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-29 12:12:54.459000 | FFAP0104
85 | 86 | FMSV2023060054 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2020-06-12 00:00:00 | EG-600WR | 7G391K122 | Gastro | 600 | 2021-06-13 00:00:00 | 2023-06-20 00:00:00 | 2023-06-23 00:00:00 | GDKT-2023060054 |  | BSA, FCT | 2038 | 2023-06-28 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023060054 | FFAP0062 | waiting confirm | 1. Less than 4 weeks after giving the quotation | Inspection | Awating Contract billing |  |  | 2023-06-29 12:12:02.266000 | FFAP0104
86 | 87 | FMSV2023060058 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2017-02-08 00:00:00 | BL-7000 | 2S101K411 | Light Source | 7000 | 2018-02-08 00:00:00 | 2023-06-22 13:13:43 | 2023-06-22 18:19:04 | GDKT-2023060058 | Other | PCB | [11 empty] | Hoang Long Clinic\FMSV2023060058 | FFAP0066 | LP/prepairing quotation | SPR Project | Inspection | Awating Parts billing |  |  | 2023-06-26 12:22:40.741000 | thongle
87 | 88 | FMSV2023060059 | private | Thanh An- Ha Noi limited company | Trang Thi | HCM | 2019-06-18 00:00:00 | EC-760ZP-V/L | 2C731K066 | Colono | 760 | 2020-06-18 00:00:00 | 2023-06-30 11:29:22 | 2023-06-30 11:57:58 | GDKT-2023060059 |  | AWB, DRY, BSA | 1581 | 2023-07-05 00:00:00 | [9 empty] | Thanh An- Ha Noi limited company\FMSV2023060059 | thongle | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-13 17:24:55.893000 | FFAP0104
88 | 89 | FMSV2023060064 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2019-05-24 00:00:00 | EC-600ZW/M | 1C694K023 | Colono | 600 | 2020-05-24 00:00:00 | 2023-06-26 00:00:00 | 2023-06-26 00:00:00 | TR-2023060064 | Major | CHA, FSA |  | FOC | [10 empty] | Thang | waiting approved |  | Inspection | Awating Contract billing |  |  | 2023-06-26 17:48:54.625000 | thang
89 | 90 | FMSV2023060065 | Government | Bai Chay Hospital | MDC | Hanoi | 2017-04-18 00:00:00 | VP-4450HD | 2V567K846 | Processor | 4450 | 2018-04-18 00:00:00 | 2023-06-26 19:18:56 | 2023-06-29 12:26:20 | GDKT-2023060065 | Other | PCB | 10698 | 2023-07-05 00:00:00 | [9 empty] | Bai Chay Hospital\FMSV2023060065 | FFAP0062 | LP/waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-12 13:53:28.510000 | FFAP0104
90 | 91 | FMSV2023060066 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2018-04-20 00:00:00 | EG-760R | 2G402K099 | Gastro | 760 | 2019-04-20 00:00:00 | 2023-07-17 12:45:38 | 2023-07-17 12:49:21 |  |  | ANGL | [12 empty] | thongle | Received |  | Inspection | PO Received |  |  | 2023-07-19 16:43:12.857000 | Nguyen
91 | 92 | FMSV2023060068 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2019-09-11 00:00:00 | EG-530WR | 5G361K065 | Gastro | 530 | 2020-09-11 00:00:00 | 2023-06-29 00:00:00 | 2023-06-30 00:00:00 | TR-2023060068 | Major | CHA, BSA |  | FOC | [9 empty] | FUJIFILM Vietnam Co., Ltd\FMSV2023060068 | Nguyen | waiting approved |  | Inspection | Awating Parts billing |  |  | 2023-06-30 11:32:29.569000 | Nguyen
92 | 93 | FMSV2023060069 | Private | MINH DUC HOSPITAL |  | HCM | 2018-12-11 00:00:00 | EG-530NW | 2G366K020 | Gastro | 530 | 2019-12-11 00:00:00 | 2023-06-29 00:00:00 | 2023-06-30 00:00:00 | GDKT-2023060069 | Major | ISA | 8672 | 2023-07-05 00:00:00 | [9 empty] | Minh Duc Hospital\FMSV2023060069 | Nguyen | waiting confirm |  | Inspection | Awating Parts billing |  |  | 2023-06-30 11:24:55.385000 | Nguyen
93 | 94 | FMSV2023070001 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2017-05-10 00:00:00 | EG-600WR | 2G391K779 | Gastro | 600 | 2018-05-10 00:00:00 | 2023-07-04 00:00:00 | 2023-07-06 00:00:00 |  | Major | BSA, FSB, FCT | 3973 | 2023-07-11 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023070001 | FFAP0070 | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-12 15:33:43.585000 | FFAP0104
94 | 95 | FMSV2023070003 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2019-01-01 00:00:00 | EG-600WR | 5G391K028 | Gastro | 600 | 2020-01-01 00:00:00 | 2023-07-04 00:00:00 | 2023-07-06 00:00:00 |  | Major | BSA, FSB, FCT, FSA, SUV | 3921 | 2023-07-11 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023070003 | FFAP0062 | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-12 15:28:21.202000 | FFAP0104
95 | 96 | FMSV2023070004 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2019-01-01 00:00:00 | EG-600WR | 2G391K945 | Gastro | 600 | 2020-07-01 00:00:00 | 2023-07-04 00:00:00 | 2023-07-06 00:00:00 |  | Major | VCA, FSA, BSA | 4110 | 2023-07-11 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023070004 | FFAP0070 | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-12 15:30:49.376000 | FFAP0104
96 | 97 | FMSV2023070005 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2016-05-18 00:00:00 | EG-600WR | 2G391K093 | Gastro | 600 |  | 2023-07-04 13:44:29 | 2023-07-06 15:51:59 | GDKT-2023070005 | Major | WJT, FSB, VCA, FSA | [11 empty] | Hanoi Medical University\FMSV2023070005 | Thang | prepairing quotation |  | Inspection | Awating Contract billing |  |  | 2023-07-12 15:25:09.520000 | FFAP0104
97 | 98 | FMSV2023070008 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2017-05-15 00:00:00 | EC-600WI | 1C692K734 | Colono | 600 | 2018-05-15 00:00:00 | 2023-07-04 15:48:16 | 2023-07-04 17:08:24 | GDKT-2023070008 | Major | FSA, BSA, VCA, FSB | 5789 | 2023-07-05 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023070008 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-12 15:06:05.873000 | FFAP0104
98 | 99 | FMSV2023070009 | Private | Hoan My Sai Gon Premier Hospital | ETC | HCM | 2015-05-17 00:00:00 | ED-530XT | 1D102K254 | Duo Scope | 530 | 2016-05-16 00:00:00 | 2023-07-04 00:00:00 | 2023-07-05 00:00:00 | GDKT-2023070009 | Major | ISA, VCA, ANGL, FSA | 12431 | 2023-07-05 00:00:00 | [9 empty] | Hoan My Sai Gon Premier Hospital\FMSV2023070009 | thongle | waiting confirm |  | Inspection | Waiting for Next Process Available |  |  | 2023-07-05 16:01:44.198000 | thongle
99 | 100 | FMSV2023070010 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2021-12-03 00:00:00 | EG-600WR | 9G391K106 | Gastro | 600 | 2022-12-03 00:00:00 | 2023-07-05 12:51:47 | 2023-07-12 13:33:50 |  |  | O, DRY | [12 empty] | Nguyen Khac Thang (Hanoi) | Completed repair | End: 18-Jul.Start: . | Repair |  | Approval | Nguyen Khac Thang (Hanoi) | 2023-07-18 16:36:47.816000 | thang
100 | 101 | FMSV2023070012 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2016-05-18 00:00:00 | EG-600WR | 2G391K208 | Gastro | 600 | 2017-05-18 00:00:00 | 2023-07-06 00:00:00 | 2023-07-12 00:00:00 | GDKT-2023070012 | Major | SUV, FSB, VCA, BSA, LPA | 4655 | 2023-07-11 00:00:00 | [9 empty] | Hanoi Medical University\FMSV2023070012 | FFAP0104 | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-12 15:31:55.889000 | FFAP0104
101 | 102 | FMSV2023070013 | Government | Bach Mai Hospital | Trang Thi | Hanoi | 2021-02-23 00:00:00 | ED-580XT | 3D127K338 | Duo Scope | 580 | 2022-03-01 00:00:00 | 2023-07-07 00:00:00 | 2023-07-12 00:00:00 |  | Major | CLN, BSA, FCT | 3017 | 2023-07-07 00:00:00 | [9 empty] | Bach Mai Hospital\FMSV2023070013 | FFAP0104 | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-12 13:48:07.054000 | FFAP0104
102 | 103 | FMSV2023070014 | Private | VIET MY GENERAL CLINIC |  | Hanoi | 2018-01-12 00:00:00 | EG-250WR5 | 1G202K621 | Gastro | 250 | 2019-01-12 00:00:00 | 2023-07-10 00:00:00 | 2023-07-12 00:00:00 |  | Major | BSA, CLN | 1775 | 2023-07-11 00:00:00 | 2023-07-19 00:00:00 | [8 empty] | Viet My General Clinic\FMSV2023070014 | FFAP0104 | waiting for part | Confirmed: 19-Jul. | Inspection | PO Received |  |  | 2023-07-12 15:20:06.643000 | FFAP0104
103 | 104 | FMSV2023070015 | Government | Northwestern Nghe An hospital |  | Hanoi | 2013-09-09 00:00:00 | EC-530LP | 4C657A022 | Colono | 530 | 2014-09-09 00:00:00 | 2023-07-10 11:53:02 | 2023-07-13 12:12:54 |  |  | FSB, FSA, VCA, CHA | [11 empty] | Northwestern Nghe An hospital\FMSV2023070015 | Thang | under inspection |  | Inspection | Awating Contract billing |  |  | 2023-07-19 19:57:09.528000 | FFAP0104
104 | 105 | FMSV2023070016 | Government | Northwestern Nghe An hospital |  | Hanoi | 2016-08-11 00:00:00 | EG-250WR5 | 1G202K277 | Gastro | 250 |  | 2023-07-10 11:54:21 | 2023-07-11 11:21:45 | GDKT-2023070016 | Major | FSA, BSA, FCT, DEC | [11 empty] | Northwestern Nghe An hospital\FMSV2023070016 | Thang | prepairing quotation |  | Inspection | Awating Contract billing |  |  | 2023-07-19 19:56:42.218000 | FFAP0104
105 | 106 | FMSV2023070017 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2019-03-19 00:00:00 | EG-530WR | 5G361k424 | Gastro | 530 | 2020-03-19 00:00:00 | 2023-07-10 12:15:43 | 2023-07-11 11:08:10 | GDKT-2023070017 | Major | BSA, LGB, FSB, FCT, VCA | 4182 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070017 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:02:19.280000 | FFAP0104
106 | 107 | FMSV2023070018 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2020-09-05 00:00:00 | EC-530WL3 | 5C643K347 | Colono | 530 | 2021-09-05 00:00:00 | 2023-07-10 12:16:56 | 2023-07-11 12:25:53 | GDKT-2023070018 | Major | DEC, DRY, BSA, DWA | 1275 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070018 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:02:38.302000 | FFAP0104
107 | 108 | FMSV2023070019 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2020-08-04 00:00:00 | EG-530WR | 8G361K200 | Gastro | 530 | 2021-08-04 00:00:00 | 2023-07-10 12:18:13 | 2023-07-12 11:50:51 | GDKT-2023070019 | Major | CHA, LGB, FSA, FCT | 6320 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070019 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:03:03.173000 | FFAP0104
108 | 109 | FMSV2023070020 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2019-03-19 00:00:00 | EG-530WR | 5G361K426 | Gastro | 530 | 2020-03-19 00:00:00 | 2023-07-10 12:19:21 | 2023-07-11 11:08:34 | GDKT-2023070020 | Major | FCT, CHA, BSA, FSA, LGB, FSB | 7342 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070020 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:03:24.756000 | FFAP0104
109 | 110 | FMSV2023070021 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2020-09-05 00:00:00 | EC-530WL3 | 5C643K365 | Colono | 530 | 2021-09-05 00:00:00 | 2023-07-10 12:22:06 | 2023-07-11 20:12:06 | GDKT-2023070021 | Major | CHA, DEC, DWA, BSA | 4703 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070021 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:04:08.587000 | FFAP0104
110 | 111 | FMSV2023070022 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2019-03-19 00:00:00 | EC-530WL3 | 3C643K193 | Colono | 530 | 2020-03-19 00:00:00 | 2023-07-10 12:23:14 | 2023-07-10 17:10:16 | GDKT-2023070022 | Major | FSA, CHA, BSA | 7273 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070022 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:04:30.870000 | FFAP0104
111 | 112 | FMSV2023070023 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2017-02-22 00:00:00 | EB-530T | 1B084K474 | Broncho | 530 | 2018-02-22 00:00:00 | 2023-07-10 12:24:40 | 2023-07-11 17:00:12 | GDKT-2023070023 | Major | VCA, CHA, FSB, PCB | 10358 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070023 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:05:03.257000 | FFAP0104
112 | 113 | FMSV2023070024 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2020-09-05 00:00:00 | EB-530T | 5B084K008 | Broncho | 530 | 2021-09-05 00:00:00 | 2023-07-10 12:26:22 | 2023-07-12 12:51:45 | GDKT-2023070024 | Major | CHA, LGB, FCT, PCB | 8052 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070024 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:05:27.107000 | FFAP0104
113 | 114 | FMSV2023070025 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2017-02-22 00:00:00 | EG-530WR | 2G361K829 | Gastro | 530 | 2018-02-22 00:00:00 | 2023-07-10 12:27:57 | 2023-07-10 19:23:04 | GDKT-2023070025 | Major | CHA, BSA, FCT, FSA, FSB | 8929 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070025 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:05:58.186000 | FFAP0104
114 | 115 | FMSV2023070026 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2020-09-05 00:00:00 | EG-530WR | 8G361K199 | Gastro | 530 | 2021-09-05 00:00:00 | 2023-07-10 12:29:11 | 2023-07-10 18:00:15 | GDKT-2023070026 | Major | AWT, FSA, FSB, BSA, FCT, CHA | 7818 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070026 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:06:24.645000 | FFAP0104
115 | 116 | FMSV2023070027 | Private | Vinmec Times City International Hospital |  | Hanoi | 2019-09-15 00:00:00 | EG-760Z | 2G403K153 | Gastro | 760 | 2020-09-15 00:00:00 | 2023-07-11 13:44:22 | 2023-07-18 19:12:30 |  |  | WJT, FCT, CHA, FSA, BSA | [12 empty] | tranminh | Received |  | Inspection | Awating Parts billing |  |  | 2023-07-18 20:06:48.306000 | thang
116 | 117 | FMSV2023070028 | Private | Nghe An Friendship General Hospital | Promed | Hanoi | 2017-02-22 00:00:00 | EG-530WR | 2G361K831 | Gastro | 530 | 2018-02-22 00:00:00 | 2023-07-12 11:56:46 | 2023-07-12 12:36:34 | GDKT-2023070028 | Major | FSB, CHA, BSA | 5412 | 2023-07-14 00:00:00 | [9 empty] | Nghe An Friendship General Hospital\FMSV2023070028 | Thang | waiting confirm |  | Inspection | Awating Contract billing |  |  | 2023-07-19 20:06:54.306000 | FFAP0104
117 | 118 | FMSV2023070032 | Private | Hoang Long Clinic | Trang Thi | Hanoi | 2017-05-24 00:00:00 | EG-760Z | 1G403K225 | Gastro | 760 | 2018-05-24 00:00:00 | 2023-07-12 18:03:08 | 2023-07-13 17:21:06 | [15 empty] | tranminh | Under repair | Start: . | QC |  | Approval | Le Van Hoan | 2023-07-17 19:38:43.366000 | FFAP0070
118 | 119 | FMSV2023070033 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2021-11-04 00:00:00 | EC-600ZW/M | 1C694K030 | Colono | 600 | 2022-11-04 00:00:00 | 2023-07-17 14:31:49 | 2023-07-17 14:39:35 |  |  | ISA | [12 empty] | Nguyen | Received |  | Inspection | PO Received |  |  | 2023-07-19 16:50:08.824000 | Nguyen
119 | 120 | FMSV2023070034 | Government | Nam Dinh General Hospital |  | Hanoi | 2010-10-22 00:00:00 | EG-530FP | 4G314A057 | Gastro | 530 |  | 2023-07-13 19:04:50 | 2023-07-18 12:35:34 |  |  | FSA, FSB, BSA, VCA | [12 empty] | thang | Received |  | Inspection | Awating Parts billing |  |  | 2023-07-18 16:05:29.057000 | FFAP0070
120 | 121 | FMSV2023070035 | Government | Nam Dinh General Hospital |  | Hanoi | 2010-10-22 00:00:00 | EC-530WI | 4C449B022 | Colono | 530 |  | 2023-07-13 19:07:15 | 2023-07-18 16:27:54.672000 |  |  | CHA, FSB, BSA, FSA, VCA | [12 empty] | thang | Received |  | Inspection | Awating Parts billing |  |  | 2023-07-18 16:34:28.035000 | FFAP0062
121 | 122 | FMSV2023070036 | Government | Nam Dinh General Hospital |  | Hanoi | 2010-10-22 00:00:00 | EC-530WI | 4C449B024 | Colono | 530 |  | 2023-07-13 19:09:12 | 2023-07-18 12:20:01 |  |  | CHA, FSA, FSB, VCA, BSA, SW | [12 empty] | thang | Received |  | Inspection | Awating Parts billing |  |  | 2023-07-18 13:43:38.095000 | FFAP0062
122 | 123 | FMSV2023070037 | Government | Nam Dinh General Hospital |  | Hanoi | 2014-12-15 00:00:00 | EG-530WR | 4G361A641 | Gastro | 530 |  | 2023-07-13 19:14:03 | 2023-07-18 16:05:50 |  |  | AWT, CHA, FSB, BSA, VCA | [12 empty] | thang | Received |  | Inspection | Awating Parts billing |  |  | 2023-07-18 16:05:58.287000 | FFAP0070
123 | 124 | FMSV2023070038 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2021-12-03 00:00:00 | EC-600WI | 7C692K030 | Colono | 600 | 2022-12-03 00:00:00 | 2023-07-14 17:03:13 | 2023-07-19 11:09:43 | [15 empty] | nguyenminh | Received |  | Repair |  | Approval | Nguyen Tuan Minh | 2023-07-19 15:38:36.474000 | FFAP0070
124 | 125 | FMSV2023070039 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2016-05-18 00:00:00 | VP-4450HD | 2V567K687 | Processor | 4450 | 2017-05-18 00:00:00 | 2023-07-14 17:06:42 |  | WTY-FFVN-2307024 |  | PCB | [12 empty] | nguyenminh | LP/Received |  | Receive | Waiting for Next Process Available |  |  | 2023-07-19 10:35:50.768000 | FFAP0062
125 | 126 | FMSV2023070040 | Government | 103 Military Hospital |  | Hanoi | 2019-02-21 00:00:00 | EC-600WI | 3C692K105 | Colono | 600 | 2020-02-21 00:00:00 | 2023-07-14 17:22:03 | 2023-07-20 10:40:17 |  |  | OSA | [12 empty] | nguyenminh | Received |  | Authorization |  | Approval |  | 2023-07-20 10:40:52.718000 | thang
126 | 127 | FMSV2023070042 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2015-12-26 00:00:00 | EC-600WI | 1C692K249 | Colono | 600 | 2016-12-26 00:00:00 | 2023-07-17 16:01:17 | 2023-07-18 18:10:02 |  | Minor | SUT | [12 empty] | Le Van Hoan | Completed repair | End: 19-Jul. | Repair |  | Approval | Le Van Hoan | 2023-07-19 15:36:53.426000 | FFAP0062
127 | 128 | FMSV2023070043 | Government | Vietnam – Cuba Donghoi Friendship Hospital | Promed | Hanoi | 2023-03-21 00:00:00 | EG-760R | KG402K677 | Gastro | 760 | 2024-03-21 00:00:00 | 2023-07-18 18:59:34.264000 |  | WTY-FFVN-2307022 |  | CHA, BSA | [12 empty] | thang | Received |  | Receive | Awating Parts billing |  |  | 2023-07-18 18:59:34.264000 | thang
128 | 129 | FMSV2023070044 | Private | No. 91 Endoscopy-Gastrointestinal-GI Scaning Test Clinic | ETC | HCM | 2019-06-10 00:00:00 | EG-760Z | 2G403K151 | Gastro | 760 | 2020-06-10 00:00:00 | 2023-07-19 16:41:58.116000 |  |  | Major | FSB, ANGL | [12 empty] | Nguyen | Received |  | Receive | Awating Parts billing |  |  | 2023-07-19 16:41:58.116000 | Nguyen
129 | 130 | FMSV2023070045 | Private | No. 91 Endoscopy-Gastrointestinal-GI Scaning Test Clinic | ETC | HCM | 2017-10-30 00:00:00 | EC-760R-V/L | 1C729K283 | Colono | 760 | 2018-10-30 00:00:00 | 2023-07-18 14:16:48 | 2023-07-18 14:17:40 |  | Minor | [13 empty] | Nguyen Thai | Completed repair | End: 18-Jul. | QC |  | Approval | Nguyen Thai | 2023-07-18 17:28:17.084000 | Nguyen
130 | 131 | FMSV2023070046 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | Hanoi | 2017-03-01 00:00:00 | EC-530WI3 | 1C642K363 | Colono | 530 |  | 2023-07-18 17:07:37 | 2023-07-18 18:42:37.578000 |  | Minor | DWA | [12 empty] | thang | Under inspection |  | Inspection |  |  |  | 2023-07-18 18:42:37.578000 | thang
131 | 132 | FMSV2023070047 | Government | Tuyen Quang General Hospital | Promed | Hanoi | 2022-03-31 00:00:00 | EG-530WR | 9G361K615 | Gastro | 530 | 2023-03-31 00:00:00 | 2023-07-18 17:08:34 | 2023-07-19 15:21:16.873000 |  |  | CHA, BSA, FCT | [12 empty] | FFAP0070 | Under inspection |  | Inspection | Waiting for Next Process Available |  |  | 2023-07-19 15:21:16.873000 | FFAP0070
132 | 133 | FMSV2023070048 | Government | Tuyen Quang General Hospital | Promed | Hanoi | 2022-01-31 00:00:00 | EC-530WL3 | 8C643K180 | Colono | 530 | 2023-01-31 00:00:00 | 2023-07-18 17:09:18.287000 |  |  |  | DWA | [12 empty] | tranminh | Received |  | Receive |  |  |  | 2023-07-18 17:09:18.287000 | tranminh
133 | 134 | FMSV2023070049 | Government | Tuyen Quang General Hospital | Promed | Hanoi | 2022-01-31 00:00:00 | EB-530S | 6B083K189 | Broncho | 530 | 2023-01-31 00:00:00 | 2023-07-18 17:10:30.973000 |  |  |  | CHA, BSA, FSA, DEC, LGB | [12 empty] | tranminh | Received |  | Receive | Waiting for Next Process Available |  |  | 2023-07-18 17:10:30.973000 | tranminh
134 | 135 | FMSV2023070050 | Government | Tuyen Quang General Hospital | Promed | Hanoi | 2015-08-28 00:00:00 | EG-600WR | 1G391K698 | Gastro | 600 | 2016-08-27 00:00:00 | 2023-07-18 17:11:41.302000 |  |  |  | FSB, CHA, BSA, PCB, VCA, FSA | [12 empty] | tranminh | Received |  | Receive | Waiting for Next Process Available |  |  | 2023-07-18 17:11:41.302000 | tranminh
135 | 136 | FMSV2023070051 | Government | Tuyen Quang General Hospital | Promed | Hanoi | 2014-09-25 00:00:00 | EC-530WM | 3C593A008 | Colono | 530 |  | 2023-07-18 17:13:05.423000 |  |  |  | FSB, PCB, BSA | [12 empty] | tranminh | Received |  | Receive | Waiting for Next Process Available |  |  | 2023-07-18 17:13:05.423000 | tranminh
136 | 137 | FMSV2023070052 | Private | Vinh International Hospital |  | HCM | 2017-09-06 00:00:00 | EG-530WR | 4G361K011 | Gastro | 530 | 2018-09-06 00:00:00 | 2023-07-19 13:03:43 | 2023-07-19 13:06:30 |  | Major | [13 empty] | Nguyen | Under repair | Start: .
137 | 138 | FMSV2023070053 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2016-11-27 00:00:00 | EC-760R-V/I | 1C728K139 | Colono | 760 | 2017-11-27 00:00:00 | 2023-07-24 10:00:30 | 2023-07-24 12:02:27 |  |  | OSA | [12 empty] | thongle | Received |  | QC
138 | 139 | FMSV2023070054 | Private | No. 91 Endoscopy-Gastrointestinal-GI Scaning Test Clinic | ETC | HCM | 2017-10-30 00:00:00 | EG-760R | 1G402K686 | Gastro | 760 | 2018-10-30 00:00:00 | [17 empty] | thongle | Received |  | Create
139 |  | FMSV2023070055 | Government | Vietnam-Sweden Uong Bi Hospital | Promed |  | 2018-05-17 00:00:00 | EG-530FP | 2G374K400 | Gastro | 530 | 2019-05-17 00:00:00 | 2023-07-20 13:24:41 | 2023-07-20 16:42:06 | WTY-FFVN-2307023R | Major | BSA |  |  |  | YES | [8 empty] | jasper | Inspection |  |  | Awating Parts billing
140 |  | FMSV2023070056 | FF asset | FUJIFILM Vietnam Co., Ltd. |  | HCM | 2019-06-01 00:00:00 | EG-530WR | 2G361K131 | Gastro | 530 | 2020-06-01 00:00:00 | 2023-07-21 10:58:51 | 2023-07-21 11:05:43.768000 |  | Major | BSA, FSA, VCA | [12 empty] | Nguyen | Inspection
141 |  | FMSV2023070057 |  | MEKONG HIGH TECH JOINT STOCK COMPANY |  | Hanoi | 2022-12-23 00:00:00 | EG-720R | 5G412K189 | Gastro | 720 | 2023-12-23 00:00:00 | 2023-07-21 17:54:07.777000 |  | WTY-FFVN-2307025 | [14 empty] | tranminh | Receive
142 |  | FMSV2023070058 |  | DONG HUNG HOSPITAL |  | Hanoi | 2019-02-01 00:00:00 | EB-530S | 2B083K071 | Broncho | 530 | 2020-02-01 00:00:00 | 2023-07-24 15:35:53.126000 | [16 empty] | thang | Receive
143 |  | FMSV2023070059 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2019-12-26 00:00:00 | EC-600WI | 5C692K024 | Colono | 600 | 2020-12-26 00:00:00 | 2023-07-24 15:37:02.357000 | [16 empty] | thang | Receive
144 |  | FMSV2023070060 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2017-05-15 00:00:00 | EG-600WR | 2G391K784 | Gastro | 600 | 2018-05-15 00:00:00 | 2023-07-24 15:38:04.993000 | [16 empty] | thang | Receive
145 |  | FMSV2023070061 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2019-01-01 00:00:00 | EG-600WR | 4G391K232 | Gastro | 600 | 2020-01-01 00:00:00 | 2023-07-24 15:38:56.935000 | [16 empty] | thang | Receive
146 |  | FMSV2023070062 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2016-05-18 00:00:00 | EG-600WR | 2G391K044 | Gastro | 600 | 2017-05-18 00:00:00 | 2023-07-24 15:39:43.573000 | [16 empty] | thang | Receive
147 |  | FMSV2023070063 | Government | Hanoi Medical University Hospital | Trang Thi | Hanoi | 2019-01-01 00:00:00 | EG-600WR | 4G391K119 | Gastro | 600 | 2020-01-01 00:00:00 | 2023-07-24 15:41:17.608000 | [16 empty] | thang | Receive
148 |  | FMSV2023070064 |  | Nam Can Tho Medical Center |  | HCM | 2022-06-10 00:00:00 | EG-530WR | 9G361K611 | Gastro | 530 | 2023-07-20 00:00:00 | 2023-07-24 16:32:50 | 2023-07-24 17:53:06.937000 |  | Major | CHA, FCT | [12 empty] | Nguyen | Inspection